## Executive Summary
PROJECT CHARTER: TINY VOICE COMMAND MODEL (VCM) FOR RASPBERRY PI 5
Standalone, 100% On-Device Neural Voice Command System with Wake-Word ('Hi' / 'Hello') Activation
Student Name: | Crizepvill F. Dumalaog |  | Target Hardware: | Raspberry Pi 5 Model B (ARM Cortex-A76 @ 2.4 GHz)
Student ID: | 202521406 |  | Target Specs: | 4GB LPDDR4X RAM, 32GB Class 10 MicroSD Storage
Course / Dept: | AI 231 (MLOps) / Dept. of Computer Science |  | Acoustic Target: | Direct Spoken Intent Classification (SIC) - 27 Classes
Institution: | University of the Philippines Diliman |  | Edge OS: | Raspberry Pi OS 64-bit (Debian Bookworm)
Date / Status: | September 2026 / Completed & Verified |  | Model Architecture: | BC-ResNet-1 (Broadcasted Residual Network with SSN)
1. Engineering Constraints & Benchmark Scorecard
Metric / Constraint | Assignment Target | Achieved / Measured | Margin / Delta | Status | Verification Method
Execution Autonomy | 100% On-Device (0 Cloud) | 100% Standalone (0 API calls) | Strict compliance | PASS | Wi-Fi disconnected loopback
Model Memory Footprint (INT8) | < 500 KB on Disk | 181.4 KB | +63.7% safety margin | PASS | os.path.getsize(model_int8.pt)
FP32 Uncompressed Model Size | < 1,000 KB | 108.0 KB | +89.2% margin | PASS | os.path.getsize(model_best.pt)
Parameter Count | Minimal edge footprint | 27,642 parameters | 99.5% smaller than Whisper | PASS | count_parameters(model)
Inference Latency (Edge CPU) | < 10.0 ms per 1.5s window | 8.44 ms (p95: 10.14 ms) | 15.6% below limit | PASS | 100-window timer benchmark
Test Accuracy (Unseen Audio) | >= 90.0% | 94.84% | +4.84% above target | PASS | Held-out test split (562 WAVs)
Validation Accuracy (Best) | >= 90.0% | 94.65% | +4.65% above target | PASS | Epoch 25 evaluation
Noise Robustness @ 20 dB SNR | >= 85.0% | 93.8% | +8.8% above target | PASS | Dynamic noise injection suite
Noise Robustness @ 10 dB SNR | >= 80.0% | 87.9% | +7.9% above target | PASS | Dynamic noise injection suite
Wake-Word Activation Support | Wake on 'Hi' / 'Hello' | Supported (2-stage FSM) | Zero false triggers in standby | PASS | simulation/test_wake_word.py
Smart Commands Covered | Top 10 Human Commands | Commands 1 to 10 (24 intents) | 100% functional actuation | PASS | 15/15 Integration tests passed
Background Rejection Precision | 100% rejection of noise | 100.0% precision | Zero false wakeups | PASS | Noise & silence test clips
2. Why BC-ResNet-1 Beats Standard Edge Solutions
Sub-Spectral Normalization (SSN): | Splits the 40 mel frequency bins into 4 sub-bands and applies independent batch normalization, preserving formant identities without parameter bloat.
Frequency Broadcasting Attention: | Computes a 1D temporal summary vector and broadcasts it multiplicatively across all spectral channels, allowing the model to learn global vocal tract transitions with only 27,642 parameters.
Two-Stage Wake State Machine: | Assistant sleeps in STANDBY mode ignoring speech commands until awakened by 'Hi' or 'Hello'. Emits an acoustic double-beep chime and Cyan LED pulse, opening a 7-second active listening window.
Real-Time Sliding Audio Buffer: | Circular AudioRingBuffer continuously pushes incoming 16kHz PCM chunks with 250ms hop, executing sub-9ms forward passes at < 5% CPU utilization on Raspberry Pi 5.

## Work Breakdown & Phases
WORK BREAKDOWN STRUCTURE (WBS) & EXECUTION PHASES
End-to-End Implementation Plan from Edge Feasibility to Raspberry Pi 5 Turnkey Deployment
WBS ID | Phase / Stage | Task Description | Deliverable / Output Artifact | Dependencies | Est. Hours | Status | Verification Criteria
1.1 | Phase 1: Feasibility & Spec | Analyze top 10 human smart-device commands from Alexa/Google Home logs | Vocabulary specification & command rank hierarchy | None | 4 | COMPLETED | 10 command categories identified
1.2 | Phase 1: Feasibility & Spec | Define edge compute constraints (Raspberry Pi 5, 4GB RAM, <500KB footprint) | Hardware constraint charter (<10ms, <500KB) | 1.1 | 3 | COMPLETED | Constraints documented in HANDOFF_INDEX.md
1.3 | Phase 1: Feasibility & Spec | Compare ASR vs Direct Spoken Intent Classification (SIC) trade-offs | Architectural decision record (BC-ResNet vs Whisper) | 1.2 | 4 | COMPLETED | Footprint reduced by >99.5%
2.1 | Phase 2: Dataset Engineering | Design phonetic phrasing bank across commands 1 to 10 + wake word | COMMAND_PHRASES mapping in source_dataset.py | 1.1 | 6 | COMPLETED | 27 classes with natural variations
2.2 | Phase 2: Dataset Engineering | Generate multi-speaker acoustic recordings using native SAPI voices | 3,420 base 16kHz WAV files across 3 acoustic voices | 2.1 | 8 | COMPLETED | David (US-M), Hazel (UK-F), Zira (US-F)
2.3 | Phase 2: Dataset Engineering | Synthesize environmental background noise pool (fan hum, babble, pink noise) | 180 noise & silence WAV files in _background_noise_ | 2.2 | 4 | COMPLETED | Realistic SNR mixing capability
2.4 | Phase 2: Dataset Engineering | Source dedicated wake-word recordings ('Hi', 'Hello', 'Hey') | 315 physical WAV files in data/dataset/wake_word | 2.2 | 5 | COMPLETED | Total dataset reaches 4,383 WAV files
3.1 | Phase 3: Architecture & Pipeline | Implement 16kHz Log-Mel feature extractor (40 filterbanks, 151 frames) | LogMelFrontend module in src/audio.py | 2.1 | 5 | COMPLETED | Exact (1, 40, 151) tensor shape verified
3.2 | Phase 3: Architecture & Pipeline | Implement Sub-Spectral Normalization (SSN) and Depthwise Convolutions | SubSpectralNorm & BroadcastResidualBlock in src/model.py | 3.1 | 8 | COMPLETED | Parameter efficiency < 30k params
3.3 | Phase 3: Architecture & Pipeline | Implement Frequency Broadcasting Attention mechanism | BC-ResNet-1 complete neural architecture | 3.2 | 6 | COMPLETED | 27,642 total learnable parameters
3.4 | Phase 3: Architecture & Pipeline | Implement thread-safe circular AudioRingBuffer with true is_filled tracking | AudioRingBuffer class in src/audio.py | 3.1 | 5 | COMPLETED | Zero-padded initial window bug prevented
4.1 | Phase 4: Training & Validation | Build PyTorch DataLoader pipeline with online SpecAugment & SNR mixing | VoiceCommandDataset class in src/dataset.py | 2.4, 3.1 | 6 | COMPLETED | Dynamic augmentation on train split
4.2 | Phase 4: Training & Validation | Execute 25-epoch GPU training run with AdamW and Cosine Annealing | Checkpoint bc_resnet_best.pt (108 KB) | 4.1, 3.3 | 8 | COMPLETED | Val acc: 94.65%, Test acc: 94.84%
4.3 | Phase 4: Training & Validation | Evaluate noise robustness across discrete SNRs (+30dB to -5dB) | SNR degradation curve & benchmark report | 4.2 | 5 | COMPLETED | 93.8% acc @ 20dB, 87.9% @ 10dB
5.1 | Phase 5: Edge Optimization | Perform INT8 post-training dynamic quantization on linear and conv layers | Optimized model bc_resnet_int8.pt (181.4 KB) | 4.2 | 4 | COMPLETED | Size beats 500KB constraint by >63%
5.2 | Phase 5: Edge Optimization | Benchmark single-window CPU inference latency over 100 consecutive frames | Latency profile histogram (Mean: 8.44 ms) | 5.1 | 4 | COMPLETED | Passes < 10.0 ms real-time limit
6.1 | Phase 6: HAL & State Machine | Implement Hardware Abstraction Layer (HAL) for physical & virtual devices | SmartAssistantHardware, VirtualHardware in src/hal.py | 1.2 | 8 | COMPLETED | ASCII OLED & virtual RGB PWM LED
6.2 | Phase 6: HAL & State Machine | Implement SmartDeviceController state machine for Commands 1 to 10 | SmartDeviceController in src/actions.py | 6.1 | 8 | COMPLETED | All 10 commands mapped to actuation
6.3 | Phase 6: HAL & State Machine | Implement two-stage wake-word state machine (STANDBY -> LISTENING) | StreamingVCMEngine in src/engine.py | 6.2, 5.1 | 6 | COMPLETED | Wake chime, Cyan glow, 7s timeout
6.4 | Phase 6: HAL & State Machine | Execute automated integration test suite covering commands and wake flow | test_all_commands.py & test_wake_word.py | 6.3 | 5 | COMPLETED | 15/15 + 5/5 tests passed (100%)
7.1 | Phase 7: Deployment & UI | Build interactive Gradio web application with live microphone capture | app.py with retro OLED & glowing RGB LED lamp | 6.3 | 10 | COMPLETED | Live audio recording & 1-click test bank
7.2 | Phase 7: Deployment & UI | Create self-contained academic course notebook with full documentation | ME2_Voice_Command_Model.ipynb (534 KB executed) | 4.2, 5.2, 6.4 | 8 | COMPLETED | All equations, loss curves, and CM embedded
7.3 | Phase 7: Deployment & UI | Package turnkey deployment folder for Raspberry Pi 5 (RP1 compatible) | rpi_deployment/ with setup_rpi.sh & vcm.service | 6.1, 7.1 | 6 | COMPLETED | Automated setup for Pi 5 4GB RAM 32GB
7.4 | Phase 7: Deployment & UI | Write physical hardware wiring & pinout guide for 40-pin GPIO | WIRING_GUIDE.md with schematics & BOM | 7.3 | 4 | COMPLETED | I2C OLED, RGB LED, active buzzer pinouts

## Command Vocabulary & Dataset
SMART DEVICE COMMAND VOCABULARY & PHYSICAL DATASET MATRIX
4,383 Physical 16 kHz WAV Recordings across 27 Classes (Commands 1 to 10 + Wake Word + Noise)
Class ID | Command Category | Class Identifier | Representative Phrasing | Train WAVs | Val WAVs | Test WAVs | Total WAVs | Actuator Output / State Change
0 | Wake-Word Activation | wake_word | 'Hello', 'Hi', 'Hey', 'Hello assistant', 'Hi there' | 236 | 39 | 40 | 315 | Double-beep chime, Cyan LED pulse, OLED 'ASSISTANT AWAKE'
1 | Cmd 1: Music Playback | play_music | 'Play music', 'Play some music', 'Start the music' | 135 | 22 | 23 | 180 | Media State = Playing, Cyan LED (0.8, 0.8), Speaker track
2 | Cmd 8: Media Control | media_pause | 'Pause', 'Pause the music', 'Stop playback' | 101 | 17 | 17 | 135 | Media State = Paused, OLED 'MEDIA PAUSED'
3 | Cmd 8: Media Control | media_resume | 'Resume', 'Continue music', 'Unpause' | 101 | 17 | 17 | 135 | Media State = Playing, OLED 'MEDIA RESUMED'
4 | Cmd 8: Media Control | media_next | 'Next', 'Next song', 'Skip track' | 101 | 17 | 17 | 135 | Buzzer beep (1200Hz), OLED 'Track 2'
5 | Cmd 8: Media Control | volume_up | 'Volume up', 'Louder', 'Increase volume' | 101 | 17 | 17 | 135 | Volume += 10%, Beep (1000Hz), OLED 'Vol: 80%'
6 | Cmd 8: Media Control | volume_down | 'Volume down', 'Quieter', 'Decrease volume' | 101 | 17 | 17 | 135 | Volume -= 10%, Beep (800Hz), OLED 'Vol: 60%'
7 | Cmd 2: Questions / Search | question_weather | 'What's the weather', 'Weather forecast', 'How is the weather' | 135 | 22 | 23 | 180 | Beep (880Hz), OLED 'Diliman, QC: 29 C Partly Cloudy'
8 | Cmd 2: Questions / Search | question_time | 'What time is it', 'Tell me the time', 'Current time' | 135 | 22 | 23 | 180 | Beep (1000Hz), OLED formatted Current Clock & Date
9 | Cmd 3: Control Lights | lights_on | 'Turn on lights', 'Switch on lights', 'Lights on' | 135 | 22 | 23 | 180 | Lights State = ON, White LED (1.0, 1.0, 1.0) 100% PWM
10 | Cmd 3: Control Lights | lights_off | 'Turn off lights', 'Switch off lights', 'Lights off' | 135 | 22 | 23 | 180 | Lights State = OFF, LED Turn OFF (0.0, 0.0, 0.0)
11 | Cmd 4: Dim / Color Lights | dim_lights_25 | 'Dim lights to 25 percent', 'Set brightness to 25 percent' | 67 | 11 | 12 | 90 | Warm Amber LED (0.25 PWM), OLED 'Brightness: 25%'
12 | Cmd 4: Dim / Color Lights | dim_lights_50 | 'Dim lights to 50 percent', 'Dim lights to half' | 101 | 17 | 17 | 135 | Warm Amber LED (0.50 PWM), OLED 'Brightness: 50%'
13 | Cmd 4: Dim / Color Lights | dim_lights_75 | 'Dim lights to 75 percent', 'Set brightness to 75 percent' | 67 | 11 | 12 | 90 | Warm Amber LED (0.75 PWM), OLED 'Brightness: 75%'
14 | Cmd 4: Dim / Color Lights | dim_lights_100 | 'Dim lights to 100 percent', 'Lights to maximum' | 101 | 17 | 17 | 135 | Warm White LED (1.00 PWM), OLED 'Brightness: 100%'
15 | Cmd 5: Set a Timer | timer_1min | 'Set a timer for 1 minute', 'Start a 1 minute timer' | 101 | 17 | 17 | 135 | Async Timer Thread, OLED Countdown, 3 Buzzer Beeps at expiry
16 | Cmd 5: Set a Timer | timer_5min | 'Set a timer for 5 minutes', 'Start a 5 minute timer' | 101 | 17 | 17 | 135 | Async Timer Thread, OLED Countdown, 3 Buzzer Beeps at expiry
17 | Cmd 5: Set a Timer | timer_10min | 'Set a timer for 10 minutes', 'Start a 10 minute timer' | 101 | 17 | 17 | 135 | Async Timer Thread, OLED Countdown, 3 Buzzer Beeps at expiry
18 | Cmd 6: Set an Alarm | alarm_set | 'Set an alarm for 7 am', 'Wake me up at 7 am' | 101 | 17 | 17 | 135 | Yellow LED indicator, Alarm State = 07:00 AM Active
19 | Cmd 7: Thermostat Control | temp_cooler | 'Make it cooler', 'Decrease temperature', 'Turn down thermostat' | 101 | 17 | 17 | 135 | Temp -= 1 F, Blue LED (Cooling mode), OLED 'COOLING'
20 | Cmd 7: Thermostat Control | temp_warmer | 'Make it warmer', 'Increase temperature', 'Turn up thermostat' | 101 | 17 | 17 | 135 | Temp += 1 F, Red LED (Heating mode), OLED 'HEATING'
21 | Cmd 7: Thermostat Control | temp_set_72 | 'Set temperature to 72 degrees', 'Thermostat 72 degrees' | 67 | 11 | 12 | 90 | Temp = 72 F, Green LED (Eco mode), OLED 'ECO AUTO'
22 | Cmd 9: Reminders & Lists | reminders_check | 'What are my reminders', 'Check my reminders', 'Read reminders' | 135 | 22 | 23 | 180 | Beep (900Hz), OLED displays top 2 active reminders
23 | Cmd 10: Calls & Messaging | call_mom | 'Call mom', 'Phone mom', 'Dial mom' | 101 | 17 | 17 | 135 | Green LED (Active call), Dial tone beep (440Hz), OLED Ringing
24 | Negative Rejection | _background_noise_ | Fan/AC motor hum, pink room noise, multi-talker babble | 67 | 11 | 12 | 90 | Zero action triggered (State remains Standby / Listening)
25 | Negative Rejection | _silence_ | Digital zero noise floor, quiet ambient baseline | 67 | 11 | 12 | 90 | Zero action triggered (State remains Standby / Listening)
TOTAL

## Raspberry Pi 5 BOM & Wiring
HARDWARE BILL OF MATERIALS (BOM) & 40-PIN GPIO SCHEMATIC
Component Specifications, Pin Mappings, and Costing for Raspberry Pi 5 Edge Smart Assistant
Item # | Component Name | Specification / Model | Qty | Interface / Bus | Raspberry Pi 5 Pin Mapping | Est. Cost (PHP) | Hardware Role / Technical Notes
1 | Single Board Computer | Raspberry Pi 5 Model B (4GB LPDDR4X RAM) | 1 | Broadcom BCM2712 | Host Computer | 4200 | Quad-core ARM Cortex-A76 @ 2.4 GHz; RP1 I/O controller
2 | Storage (MicroSD) | SanDisk Ultra 32GB MicroSDHC UHS-I (Class 10) | 1 | MicroSD Slot | Storage Bus | 350 | Contains Raspberry Pi OS 64-bit, PyTorch environment, models
3 | Power Supply | Official Raspberry Pi 27W USB-C Power Adapter | 1 | USB-C Port | 5.1V / 5.0A Power | 750 | Provides clean 5A power preventing CPU throttling
4 | Microphone In | Mini USB Microphone / Plug-and-Play Lavalier | 1 | USB 2.0 / 3.0 | ALSA Audio In (/dev/snd) | 180 | 16 kHz mono acoustic capture; standard USB audio class
5 | Speaker Out | USB Audio Speaker / Mini USB Sound Adapter | 1 | USB 2.0 / 3.0 | ALSA Audio Out (/dev/snd) | 250 | RPi 5 has no 3.5mm analog jack; USB audio output is required
6 | OLED Display | 0.96 inch I2C SSD1306 Monochrome OLED (128x64) | 1 | Hardware I2C Bus 1 | VCC: Pin 01 (3.3V), GND: Pin 09, SDA: Pin 03 (GPIO 2), SCL: Pin 05 (GPIO 3) | 220 | Address 0x3C; displays 4-line smart assistant state and metrics
7 | RGB PWM LED | Common-Cathode 5mm RGB LED (Diffused) | 1 | Hardware PWM GPIO | Red: Pin 11 (GPIO 17), Green: Pin 13 (GPIO 27), Blue: Pin 15 (GPIO 22), Cathode: Pin 06 (GND) | 35 | Smooth color shifting (Cyan=Wake/Music, White=Lights, Blue=AC, Red=Heat)
8 | Resistors | 330 Ohm 1/4W Metal Film Resistors | 3 | In-line Passive | In series with Red, Green, and Blue LED anode pins | 15 | Current limiting; protects GPIO pins from overcurrent (>16mA)
9 | Active Buzzer | 5V / 3.3V Active Piezo Buzzer | 1 | Digital GPIO | Positive (+): Pin 16 (GPIO 23), Negative (-): Pin 20 (GND) | 45 | Emits acoustic feedback, double-beep wake chime, and timer alerts
10 | Breadboard & Wires | Half-size 400-point Breadboard + 20cm Dupont M-F wires | 1 | Wiring Harness | Links Pi 40-pin header to breadboard components | 120 | Zero-soldering modular prototyping setup
TOTAL ESTIMATED BOM

## Edge Performance & Benchmarks
RASPBERRY PI 5 (ARM CORTEX-A76) BENCHMARK PROFILE
Measured Latency, Memory Footprint, and Noise Degradation Curves
1. Pipeline Stage Latency Decomposition (per 1.5s Audio Window)
Pipeline Stage | Operation / Algorithm | Computation Type | Average Latency (ms) | Share (%) | Real-Time Feasibility
Stage 1: Circular Ring Buffer Ingestion | Push 4,000 PCM samples (250ms hop) into FIFO array | Memory Roll / Slice | 0.12 | 1.4% | Instantaneous
Stage 2: Acoustic Log-Mel Frontend | STFT (512 FFT, 400 win, 160 hop) + 40 Mel Filterbanks | FFT / Float32 Matrix Mult | 2.14 | 25.4% | Sub-3ms
Stage 3: BC-ResNet-1 Forward Pass | Depthwise Separable Convolutions + SSN + Attention | INT8 / Quantized GEMM | 5.62 | 66.6% | Sub-6ms on CPU
Stage 4: Softmax & Confidence Filter | Softmax vector reduction, threshold comparison (>=0.55) | Vector Reduction | 0.08 | 0.9% | Negligible
Stage 5: State Machine & HAL Actuation | Debounce check, I2C OLED update, PWM duty cycle dispatch | GPIO / I2C Bus I/O | 0.48 | 5.7% | Non-blocking async
TOTAL END-TO-END PIPELINE LATENCY |  |  |  | 100.0% | PASS (< 10.0 ms Real-Time Limit)
2. Raspberry Pi 5 System Resource Utilization
Resource Category | Target Hardware Limit | Peak During Continuous Inference | Idle / Standby | Assessment
CPU Utilization (1 Core) | 100% of 1 Cortex-A76 core | 8.2% CPU (during 250ms hop inference) | < 1.5% CPU | Extremely light; 3 cores free
Overall Quad-Core CPU Load | 100% (4 cores @ 2.4 GHz) | 2.1% total system CPU | 0.4% total system CPU | Negligible thermal impact
RAM Consumption (Resident) | 4,096 MB LPDDR4X | 148 MB (including PyTorch & ALSA buffers) | 92 MB | Uses < 4% of available RAM
MicroSD Storage Occupancy | 32,768 MB (32 GB) | 181.4 KB (model) + 42 MB (venv/code) | N/A | Uses < 0.2% of 32GB storage
Operating Temperature | < 80 C (Thermal throttle limit) | 44.5 C (with active cooling fan) | 38.2 C | Operates well below throttle line